## Product Backlog
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | To Do/Planned | On Deck | Development | Testing | Complete | Not Delivered/Late | Still in PBL | Acceptance Critera | Abbreviation | Definition
F08 | Login only available to enrolled students | 1 | U01/SU01/U22 |  | Iteration 1 |  | x | [6 empty] | Fxx | Feature
U01 | As a user, I can create an account if I am a csuf student in order participate on the website. | 1 | F08 | Need to use CSUF email to register, first name, last name, username/password | Iteration 1 |  | x | [6 empty] | SFxx | Sub-Feature
U03 | As a user, I can scroll through the web to see the different items. | 1 | F05 |  | Iteration 1 |  | x | [6 empty] | Uxx | User Story
U22 | As a user I am able to login with CSUF email/ username/ password | 1 | F08 |  | Iteration 1 |  | x | [6 empty] | Suxx | Sub-User Story
F05 | Browse Categories of items for sale | 2 | U03 |  | Iteration 1 |  | x | [7 empty] | Current Working Items
SU01 | As a user, I can create an account using school email | 1 | F08 | Associated with U01 | Iteration 1 |  | x | [7 empty] | Completed
T-Special | Watch Amazon Clone Video | 1 |  | See acceptance criteria | Iteration 1 |  | x | [5 empty] | watch and follow along with associated sections on the video, complete by March 07 2022 EOD |  | deadline missed
T01 | Integrate Database into website | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  | x | [5 empty] | all registration information has to be saved successfully |  | reopened issue
T02 | Create Account Registration Page | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  | x | [5 empty] | Following information has to be successfully entered: First/Last Name, CSUF email, Username, Password. All information entered has to be saved into the database. All entered emails have to meet the following criteria: @csu.fullerton.edu & email is currently not in use
T03 | Create Login Page | 1 | F08/U22 | See acceptance criteria | Iteration 1 |  | x | [5 empty] | Following information has to be successfully entered: CSUF email field, Password field, login button, create account button (will link to acct registration page).
T04 | Check if login information works | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  | x | [5 empty] | checking database if entered info matches with database info
T05 | Create a Welcome/ Home Page | 1 | F05/U03 | See acceptance criteria | Iteration 1 |  | x | [5 empty] | Screen will appear when a user has successfully logged in
F03 | Post Items for Sale | 1 |  |  |  | x
F01 | Bid on Items | 1 |  |  |  | x
F02 | Review Sellers | 2 |  |  |  | x
F04 | Chat with sellers/customers through app | 1 |  |  |  | x
F06 | Comment on items | 3 |  |  |  | x
F07 | Search for specific products / sellers | 2 |  |  |  | x
F09 | Tuffy AI customer service chat | 4 |  |  |  | x
SF01 | Filter item search by categories | 2 |  |  |  | x
F10 | Find active sellers on campus (map function) | 3 |  |  |  | x
F11 | Drop location as active seller | 3 |  |  |  | x
F12 | Venmo/Zelle/Apple pay/ etc integrated into app | 3 |  |  |  | x
F13 | Automating moving listings through different categories | 4 |  |  |  | x
F14 | Review Customers | 2 |  |  |  | x
F15 | Physical 'store' for trade meetups (money for goods) | 4 |  |  |  | x
F16 | Automatic transfer of money to back acct | 3 |  |  |  | x
F17 | Seller able to choose if cash purchases are allowed | 1 |  |  |  | x
U02 | As a user, I can message sellers so that I can talk to them about the item I am interested in. | 1 |  |  |  | x
U04 | As a user, I can post a picture with a description of the item I am trying to sell. | 1 |  |  |  | x
U05 | As a user, I can have a profile page that shows the items that I am selling. | 1 |  |  |  | x
U07 | As a user, I can mark an item as sold and delete it from the marketplace. | 1 |  |  |  | x
U13 | As a user, I am able to set what type of payment methods I prefer | 1 |  |  |  | x
U17 | A verified user is able to post an item they want to sell. | 1 |  | We take a CSUF email and verify |  | x
U19 | As a user, I can purchase products from sellers | 1 |  |  |  | x
U21 | As a user I can change my password | 1 |  |  |  | x
U06 | As a user, I can organize the items by different categories such as most popular, recent, oldest, etc. | 2 |  |  |  | x
U09 | As a user, I can favorite items that I am interested to view later | 2 |  |  |  | x
U15 | As a user, I can browse my favorite items page | 2 |  |  |  | x
U08 | As a user, I can view a map that shows relative location of the seller | 3 |  |  |  | x
U10 | As a user, I can set a location to view items listed in that area | 3 |  |  |  | x
U11 | As a user, I have a digital wallet where the money from the items I sold are stored | 3 |  |  |  | x
U12 | As a user, I am able to transfer that money from my digital wallet to my bank account | 3 |  |  |  | x
U16 | As a user, I can read reviews other users have left on a sellers page, and I can leave my own review | 3 |  |  |  | x
SU02 | As a user, I can add their auto payment info | 3 |  | Associated with U11-U12 |  | x
U20 | As a user, I can share product listing on social media | 4 |  |  |  | x
U18 | as a user I am able to see similar/recommended items | 5 |  | AI! |  | x
U14 | As a user, I can search for a specific items and browse through results related to my search | 1 or 2 |  |  |  | x