## Product Backlog
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Estimated 'Value' | To Do/Planned | On Deck | Development | Testing | Complete | Not Delivered/Late | Still in PBL | Acceptance Critera | Abbreviation | Definition
F02 | Review Sellers | 2 |  |  |  |  | x
F04 | Chat with sellers/customers through app | 1 |  |  |  |  | x
F09 | Tuffy AI customer service chat | 4 |  |  |  |  | x
F10 | Find active sellers on campus (map function) | 3 |  |  |  |  | x
F11 | Drop location as active seller | 3 |  |  |  |  | x
F12 | Venmo/Zelle/Apple pay/ etc integrated into app | 3 |  |  |  |  | x
F13 | Automating moving listings through different categories | 4 |  |  |  |  | x
F14 | Review Customers | 2 |  |  |  |  | x
F15 | Physical 'store' for trade meetups (money for goods) | 4 |  |  |  |  | x
F16 | Automatic transfer of money to back acct | 3 |  |  |  |  | x
F17 | Seller able to choose if cash purchases are allowed | 1 |  |  |  |  | x
U02 | As a user, I can message sellers so that I can talk to them about the item I am interested in. | 1 |  |  |  |  | x
U06 | As a user, I can organize the items by different categories such as most popular, recent, oldest, etc. | 2 | F07 |  |  |  | x
U07 | As a user, I can mark an item as sold and delete it from the marketplace. | 1 |  |  |  |  | x
U08 | As a user, I can view a map that shows relative location of the seller | 3 |  |  |  |  | x
U09 | As a user, I can favorite items that I am interested to view later | 2 |  |  |  |  | x
U10 | As a user, I can set a location to view items listed in that area | 3 |  |  |  |  | x
U11 | As a user, I have a digital wallet where the money from the items I sold are stored | 3 |  |  |  |  | x
U12 | As a user, I am able to transfer that money from my digital wallet to my bank account | 3 |  |  |  |  | x
U13 | As a user, I am able to set what type of payment methods I prefer | 1 | F08 |  |  |  | x
U14 | As a user, I can search for a specific items and browse through results related to my search | 1 or 2 | SF01 |  |  |  | x
U15 | As a user, I can browse my favorite items page | 2 |  |  |  |  | x
U16 | As a user, I can read comments other users have left on a sellers page, and I can leave my own comments | 3 | F06 |  |  |  | x
U18 | as a user I am able to see similar/recommended items | 5 |  | AI! |  |  | x
U19 | As a user, I can bid on products from sellers | 1 | F01 |  |  |  | x
U20 | As a user, I can share product listing on social media | 4 |  |  |  |  | x
U21 | As a user I can change my password | 1 |  |  |  |  | x
U22 | As a user, I can add their auto payment info | 3 |  | Associated with U11-U12 |  |  | x
U23 | As a user, I am able to search for a specific item or seller | 2 | F07 |  |  |  | x

## Completed Items
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Acceptance Criteria
F08 | Login only available to enrolled students | 1 | U01/SU01/U22/U13/U17 | U13&U17 planned for Iteration 2 | Iteration 1
SU01 | As a user, I can create an account using school email | 1 | F08 | Associated with U01 | Iteration 1
U01 | As a user, I can create an account if I am a csuf student in order participate on the website. | 1 | F08 | Need to use CSUF email to register, first name, last name, username/password | Iteration 1
U03 | As a user, I can scroll through the web to see the different items. | 1 | F05 |  | Iteration 1
U22 | As a user I am able to login with CSUF email/ username/ password | 1 | F08 |  | Iteration 1
F05 | Browse Categories of items for sale | 2 | U03 |  | Iteration 1
F03 | Post Items for Sale | 1 | U04/U05 |  | Iteration 2
SF01 | Filter item search by categories | 2 | U14 |  | Iteration 2
U05 | As a user, I have a fully operational profile page | 1 | F01/F03/T10/T11/T12/T13/T14/T15/T16 |  | Iteration 3
U04 | As a user, I can post a picture with a description of the item I am trying to sell. | 1 | F01/F03 |  | Iteration 3
F01 | Bid on Items | 1 | U04/U05/U19
F07 | Search for specific products / sellers | 2 | U06/U23/U24
F06 | Comment on items | 3 | U16
U24 | As a user I can visit a page dedicated to each category of items | 2 | F07