## Product Backlog
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Estimated 'Value' | To Do/Planned | On Deck | Development | Testing | Complete | Not Delivered/Late | Still in PBL | Acceptance Critera | Abbreviation | Definition
F02 | Review Sellers | 2 |  |  |  |  | x
F04 | Chat with sellers/customers through app | 1 |  |  |  |  | x
F09 | Tuffy AI customer service chat | 4 |  |  |  |  | x
F10 | Find active sellers on campus (map function) | 3 |  |  |  |  | x
F11 | Drop location as active seller | 3 |  |  |  |  | x
F12 | Venmo/Zelle/Apple pay/ etc integrated into app | 3 |  |  |  |  | x
F13 | Automating moving listings through different categories | 4 |  |  |  |  | x
F14 | Review Customers | 2 |  |  |  |  | x
F15 | Physical 'store' for trade meetups (money for goods) | 4 |  |  |  |  | x
F16 | Automatic transfer of money to back acct | 3 |  |  |  |  | x
F17 | Seller able to choose if cash purchases are allowed | 1 |  |  |  |  | x
U02 | As a user, I can message sellers so that I can talk to them about the item I am interested in. | 1 |  |  |  |  | x
U06 | As a user, I can organize the items by different categories such as most popular, recent, oldest, etc. | 2 | F07 |  |  |  | x
U07 | As a user, I can mark an item as sold and delete it from the marketplace. | 1 |  |  |  |  | x
U08 | As a user, I can view a map that shows relative location of the seller | 3 |  |  |  |  | x
U09 | As a user, I can favorite items that I am interested to view later | 2 |  |  |  |  | x
U10 | As a user, I can set a location to view items listed in that area | 3 |  |  |  |  | x
U11 | As a user, I have a digital wallet where the money from the items I sold are stored | 3 |  |  |  |  | x
U12 | As a user, I am able to transfer that money from my digital wallet to my bank account | 3 |  |  |  |  | x
U13 | As a user, I am able to set what type of payment methods I prefer | 1 | F08 |  |  |  | x
U14 | As a user, I can search for a specific items and browse through results related to my search | 1 or 2 | SF01 |  |  |  | x
U15 | As a user, I can browse my favorite items page | 2 |  |  |  |  | x
U16 | As a user, I can read comments other users have left on a sellers page, and I can leave my own comments | 3 | F06 |  |  |  | x
U18 | as a user I am able to see similar/recommended items | 5 |  | AI! |  |  | x
U19 | As a user, I can bid on products from sellers | 1 | F01 |  |  |  | x
U20 | As a user, I can share product listing on social media | 4 |  |  |  |  | x
U21 | As a user I can change my password | 1 |  |  |  |  | x
U22 | As a user, I can add their auto payment info | 3 |  | Associated with U11-U12 |  |  | x
U23 | As a user, I am able to search for a specific item or seller | 2 | F07 |  |  |  | x

## Sprint Backlog
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Estimated 'Value' | Acceptance Critera
T09 | Create a rudimentary search function | 1 | F01/F03/U03/U04/U19/SF01/U14 |  | Iteration 2 |  | Following information has to be successfully entered: First/Last Name, CSUF email, Username, Password. All information entered has to be saved into the database. All entered emails have to meet the following criteria: @csu.fullerton.edu & email is currently not in use
T06 | Create user profile homepage | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | User can access their pay data, username, password, bio
T07 | Categorize posted items | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | User is able to post an item to sell, and this will be sent to the homepage.
T08 | Create a rudimentary homepage | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | Once a sales post is created and saved, the item should be saved into the database and should appear on the homescreen afterwards, the more recent the sales post, the closer to the top left of the screen the post will be
T10 | Make a profile pic input | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | User is able to fill in information about themselves and upload a photo, all items have to be fully accepted for test to pass.
T11 | Make fillable textboxes for personal information | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | User is able to fill in information about themselves and upload a photo, all items have to be fully accepted for test to pass.
T12 | Save all entered information to database | 1 | F01/F03/U05/U04 |  | Iteration3 |  | once all info is entered it is saved into firebase successfully
T13 | retrieve all saved info from database and display on profile page | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | all information is recovered and displayed properly on the profile page
T14 | make nice UI for profile page | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | make page pretty and all centered
T15 | fix UI for login page | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | make page pretty and all centered
T16 | fix UI for sales submission page | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | make page pretty and all centered
T17 | Save uploaded item in firebase | 1 | F01/F03/U05/U04 |  | Iteration 3 |  | When the user uploads an item to post on the homepage, the item datat will be stored to firebase
T18 | Create a page for books category | 1 | U24 |  | Iteration 4 |  | Hard code items from this category, all items and relevant information must be aligned properly
T19 | Create a page for tech category | 1 | U24 |  | Iteration 4 |  | Hard code items from this category, all items and relevant information must be aligned properly
T20 | Create a page for clothing category | 1 | U24 |  | Iteration 4 |  | Hard code items from this category, all items and relevant information must be aligned properly
T21 | Create a page for exercise gear | 1 | U24 |  | Iteration 4 |  | Hard code items from this category, all items and relevant information must be aligned properly
T22 | Create a page for collectibles category | 1 | U24 |  | Iteration 4 |  | Hard code items from this category, all items and relevant information must be aligned properly
T23 | Connect books page to homepage and database | 1 | U24 |  | Iteration 4 |  | All links between pages work properly and route correctly
T24 | Connect tech page to homepage and database | 1 | U24 |  | Iteration 4 |  | All links between pages work properly and route correctly
T25 | Connect clothing page to homepage and database | 1 | U24 |  | Iteration 4 |  | All links between pages work properly and route correctly
T26 | Connect exercise gear page to homepage and database | 1 | U24 |  | Iteration 4 |  | All links between pages work properly and route correctly
T27 | Connect collectibles page to homepage and database | 1 | U24 |  | Iteration 4 |  | All links between pages work properly and route correctly

## Completed Items
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Estimated 'Value' | Acceptance Criteria
T-Special | Watch Amazon Clone Video | 1 |  | See acceptance criteria | Iteration 1 |  | watch and follow along with associated sections on the video, complete by March 07 2022 EOD
T01 | Integrate Database into website | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  | all registration information has to be saved successfully
T04 | Check if login information works | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  | checking database if entered info matches with database info
F08 | Login only available to enrolled students | 1 | U01/SU01/U22/U13/U17 | U13&U17 planned for Iteration 2 | Iteration 1
SU01 | As a user, I can create an account using school email | 1 | F08 | Associated with U01 | Iteration 1
T03 | Create Login Page | 1 | F08/U22 | See acceptance criteria | Iteration 1 |  | Following information has to be successfully entered: CSUF email field, Password field, login button, create account button (will link to acct registration page).
T05 | Create a Welcome/ Home Page | 1 | F05/U03 | See acceptance criteria | Iteration 1 |  | Screen will appear when a user has successfully logged in
U01 | As a user, I can create an account if I am a csuf student in order participate on the website. | 1 | F08 | Need to use CSUF email to register, first name, last name, username/password | Iteration 1
U03 | As a user, I can scroll through the web to see the different items. | 1 | F05 |  | Iteration 1
U22 | As a user I am able to login with CSUF email/ username/ password | 1 | F08 |  | Iteration 1
F05 | Browse Categories of items for sale | 2 | U03 |  | Iteration 1
F03 | Post Items for Sale | 1 | U04/U05 |  | Iteration 2 | 3
SF01 | Filter item search by categories | 2 | U14 |  | Iteration 2 | 3
T02 | Create Account Registration Page | 1 | F08/U01 | See acceptance criteria | Iteration 2
U05 | As a user, I have a fully operational profile page | 1 | F01/F03/T10/T11/T12/T13/T14/T15/T16 |  | Iteration 3 | 3
U04 | As a user, I can post a picture with a description of the item I am trying to sell. | 1 | F01/F03 |  | Iteration 3 | 3
F01 | Bid on Items | 1 | U04/U05/U19
F07 | Search for specific products / sellers | 2 | U06/U23/U24
F06 | Comment on items | 3 | U16
U24 | As a user I can visit a page dedicated to each category of items | 2 | F07 |  |  | 3