## Product Backlog
ID | Description | Rank | Associated with Feature/Task/Story | Notes: | Planned Iteration | Estimated 'Value' | To Do/Planned | On Deck | Development | Testing | Complete | Not Delivered/Late | Still in PBL | Acceptance Critera | Abbreviation | Definition
T-Special | Watch Amazon Clone Video | 1 |  | See acceptance criteria | Iteration 1 | [5 empty] | x |  |  | watch and follow along with associated sections on the video, complete by March 07 2022 EOD | Fxx | Feature
T01 | Integrate Database into website | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  |  |  |  | x |  |  |  | all registration information has to be saved successfully | SFxx | Sub-Feature
T04 | Check if login information works | 1 | F08/U01 | See acceptance criteria | Iteration 1 |  |  |  |  | x |  |  |  | checking database if entered info matches with database info | Uxx | User Story
F08 | Login only available to enrolled students | 1 | U01/SU01/U22/U13/U17 | U13&U17 planned for Iteration 2 | Iteration 1 |  |  |  |  | x |  |  |  |  | Suxx | Sub-User Story
SU01 | As a user, I can create an account using school email | 1 | F08 | Associated with U01 | Iteration 1 |  |  |  |  | x | [5 empty] | Current Working Items
T03 | Create Login Page | 1 | F08/U22 | See acceptance criteria | Iteration 1 |  |  |  |  | x |  |  |  | Following information has to be successfully entered: CSUF email field, Password field, login button, create account button (will link to acct registration page). |  | Completed
T05 | Create a Welcome/ Home Page | 1 | F05/U03 | See acceptance criteria | Iteration 1 |  |  |  |  | x |  |  |  | Screen will appear when a user has successfully logged in |  | deadline missed
U01 | As a user, I can create an account if I am a csuf student in order participate on the website. | 1 | F08 | Need to use CSUF email to register, first name, last name, username/password | Iteration 1 |  |  |  |  | x | [5 empty] | reopened issue
U03 | As a user, I can scroll through the web to see the different items. | 1 | F05 |  | Iteration 1 |  |  |  |  | x | [5 empty] | planned for upcoming iteration
U22 | As a user I am able to login with CSUF email/ username/ password | 1 | F08 |  | Iteration 1 |  |  |  |  | x
F05 | Browse Categories of items for sale | 2 | U03 |  | Iteration 1 |  |  |  |  | x
T02 | Create Account Registration Page | 1 | F08/U01 | See acceptance criteria | Iteration 2 |  | x | [6 empty] | Following information has to be successfully entered: First/Last Name, CSUF email, Username, Password. All information entered has to be saved into the database. All entered emails have to meet the following criteria: @csu.fullerton.edu & email is currently not in use
F03 | Post Items for Sale | 1 | U04/U05 |  | Iteration 2 | 3 | x
U04 | As a user, I can post a picture with a description of the item I am trying to sell. | 1 | F01/F03 |  | Iteration 2 | 3 | x
U05 | As a user, I can have a profile page that shows the items that I am selling. | 1 | F01/F03 |  | Iteration 2 | 3 | x
U13 | As a user, I am able to set what type of payment methods I prefer | 1 | F08 |  | Iteration 2 | 2 | x
U14 | As a user, I can search for a specific items and browse through results related to my search | 1 or 2 | SF01 |  | Iteration 2 | 3 | x
SF01 | Filter item search by categories | 2 | U14 |  | Iteration 2 | 3 | x
T06 | Create user profile homepage | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | x | [6 empty] | User can access their pay data, username, password, bio
T07 | Categorize posted items | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | x | [6 empty] | User is able to post an item to sell, and this will be sent to the homepage.
T08 | Create a rudimentary homepage | 1 | F01/F03/U03/U04/U19 |  | Iteration 2 |  | x | [6 empty] | Once a sales post is created and saved, the item should be saved into the database and should appear on the homescreen afterwards, the more recent the sales post, the closer to the top left of the screen the post will be
T09 | Create a rudimentary search function | 1 | F01/F03/U03/U04/U19/SF01/U14 |  | Iteration 2 |  | x | [6 empty] | Search bar will allow user to search via category (ie: textbook, clothes, shoes, etc). Items should be correctly associated with the search key (nothing too complicated)
F01 | Bid on Items | 1 | U04/U05/U19
U19 | As a user, I can bid on products from sellers | 1 | F01
F04 | Chat with sellers/customers through app | 1 |  |  |  |  | x
F17 | Seller able to choose if cash purchases are allowed | 1 |  |  |  |  | x
U02 | As a user, I can message sellers so that I can talk to them about the item I am interested in. | 1 |  |  |  |  | x
U07 | As a user, I can mark an item as sold and delete it from the marketplace. | 1 |  |  |  |  | x
U21 | As a user I can change my password | 1 |  |  |  |  | x
F02 | Review Sellers | 2 |  |  |  |  | x
F07 | Search for specific products / sellers | 2 |  |  |  |  | x
F14 | Review Customers | 2 |  |  |  |  | x
U06 | As a user, I can organize the items by different categories such as most popular, recent, oldest, etc. | 2 |  |  |  |  | x
U09 | As a user, I can favorite items that I am interested to view later | 2 |  |  |  |  | x
U15 | As a user, I can browse my favorite items page | 2 |  |  |  |  | x
F06 | Comment on items | 3 |  |  |  |  | x
F10 | Find active sellers on campus (map function) | 3 |  |  |  |  | x
F11 | Drop location as active seller | 3 |  |  |  |  | x
F12 | Venmo/Zelle/Apple pay/ etc integrated into app | 3 |  |  |  |  | x
F16 | Automatic transfer of money to back acct | 3 |  |  |  |  | x
SU02 | As a user, I can add their auto payment info | 3 |  | Associated with U11-U12 |  |  | x
U08 | As a user, I can view a map that shows relative location of the seller | 3 |  |  |  |  | x
U10 | As a user, I can set a location to view items listed in that area | 3 |  |  |  |  | x
U11 | As a user, I have a digital wallet where the money from the items I sold are stored | 3 |  |  |  |  | x
U12 | As a user, I am able to transfer that money from my digital wallet to my bank account | 3 |  |  |  |  | x
U16 | As a user, I can read reviews other users have left on a sellers page, and I can leave my own review | 3 |  |  |  |  | x
F09 | Tuffy AI customer service chat | 4 |  |  |  |  | x
F13 | Automating moving listings through different categories | 4 |  |  |  |  | x
F15 | Physical 'store' for trade meetups (money for goods) | 4 |  |  |  |  | x
U20 | As a user, I can share product listing on social media | 4 |  |  |  |  | x
U18 | as a user I am able to see similar/recommended items | 5 |  | AI! |  |  | x